## Slide 1
DOMO
Knowledge Base Restructure
Transforming a feature encyclopedia into a narrative-driven product story — meeting users where they are.
June 2026 · Domo Documentation Team

## Slide 2
The Problem
"We have ~1,822 articles — 70% task-oriented how-tos — and almost none explain what Domo is, how its pieces fit together, or where to go next."
1,822
Total KB Articles
~70%
How-To Guides Only
~2%
Tutorials & Explanations
335
Nav Groups (22× too many)
Content Type Gap
Tutorial
Walk user through X for the first time
~5
How-To Guide
Task-focused procedures
~1,280
Reference
Definitions & technical lookups
~270
Explanation
Conceptual 'why it works this way'
~20
Structural Issues
66% of filenames are opaque Zendesk numeric IDs
0 'What is X?' concept articles for any core product area
Only 4 role-based getting-started guides (need 6+)
No section hubs — every article is a navigation dead end
800+ connector articles with no organizing hub or category
3 overlapping Workbench sections (Enterprise / 5 / 4)

## Slide 3
Vision & Framework
Transform the Domo KB from a feature encyclopedia into a narrative-driven product story — one that meets users where they are and guides them along a clear path to competency and mastery.
The Diátaxis Framework
Structure content by user need-state, not product feature
Tutorial
Learning → first-time walkthrough
Have: ~5 Target: 20+
How-To Guide
Doing → accomplish a specific task
Have: ~1,280 ✓
Reference
Looking up → definitions & specs
Have: ~270 ✓
Explanation
Understanding → why it works this way
Have: ~20 Target: 30+
The Domo Story Arc
Every section has a clear place; users always see where to go next
1
What is Domo?
2
First Login
3
Bring In Data
4
Manage Data
5
Prepare & Transform Data
6
Analyze & Visualize
7
Share & Act
8
Build & Automate
9
Govern & Administer
10
Go Deeper (AI · Dev · Advanced)
Design Principles:
Progressive Disclosure
Topic Cluster Hubs
Role-Based Entry Points
Systematic Interlinking

## Slide 4
New Information Architecture: 12 Content Pillars
Collapsing 335 navigation groups into 12 coherent, story-driven sections
1
Getting Started
34 existing · 5 new
Priority: Critical
2
Connect & Bring In Data
1,050 existing · 4 new
Priority: Medium
3
Manage Data
0–31 existing · 3 new
Priority: Critical
4
Prepare & Transform Data
101 existing · 4 new
Priority: Critical
5
Analyze & Visualize
230 existing · 4 new
Priority: Critical
6
Build Apps & Automate
106 existing · 3 new
Priority: Medium
7
Share & Collaborate
51 existing · 2 new
Priority: Medium
8
AI & Data Science
41 existing · 3 new
Priority: Medium
9
Administer & Govern
72 existing · 3 new
Priority: Medium
10
Develop & Integrate
5 existing · 4 new
Priority: High
11
Release Notes
65 existing
Priority: —
12
Archive
64 articles
Priority: —
Priority:
Critical — write now
High — severely thin
Medium — next sprint
No new articles needed

## Slide 5
What We're Building: ~33 New 'Glue' Articles
Synthesize from existing how-tos first — procedural articles already contain most conceptual raw material.
Tier 1 — Story Entry Points
What is Domo?
Getting Started for Admins
Getting Started for App Builders
Getting Started for Developers
Tier 2 — Core Concept Articles
What is a DataSet?
What is Magic ETL?
What is a DataFlow?
What is a Card?
What is a Dashboard?
What is Beast Mode?
What is App Studio?
What is an Alert?
What is a Connector?
What is Domo AI?
What is Workbench?
Tier 3 — Section Hub Articles
Connect & Bring In Data Overview
Prepare & Transform Data Overview
Analyze & Visualize Overview
Build Apps & Automate Overview
Share & Collaborate Overview
AI & Data Science Overview
Administer & Govern Overview
Develop & Integrate Overview
4 Articles Require PM Sign-off Before Writing
How Data Flows Through Domo
Canonical end-to-end pipeline narrative
Choosing the Right Data Prep Tool
ETL vs SQL vs Python positioning
Understanding DataSet Joins & Relationships
Use-case decision guidance
Domo for Mobile Overview
Confirm current mobile feature scope

## Slide 6
Execution Roadmap: 7 Phases · 6–8 Weeks
1
Audit & Inventory
• Build machine-readable catalog of all 1,822 articles
• Classify by Diátaxis type (tutorial/how-to/reference/explanation)
• Identify orphans, near-duplicates, and content gaps
1–2 days · Script + Agent · COMPLETE
2
IA Redesign
• Finalize 12-pillar structure and hub-and-spoke patterns
• Resolve 9 open decisions (D1–D9)
• Lock connector/CDW/writeback section framing
2–3 days · Human + Agent · COMPLETE
3a
Content Creation — New Articles
• Write ~29 synthesizable glue articles (skills: new-kb-article, new-overview-article)
• Synthesize from existing how-tos; no raw invention
• Must author in main session (sub-agent write-block)
2–3 weeks · Human (main session)
3b
Article Upgrades (~200 articles)
• Add concept intro to every article missing one
• Append Next Steps (2–4 forward links) to every article
• Agent-parallelizable in batches of 25–50 (Edit only)
2–3 days · Agent (batch) · Parallel with 3a
4
Consolidation & Retirement
• Merge Workbench version variants; collapse old release notes
• Archive Workbench 4 (37 EOL articles)
• Retire stubs < 100 words and deprecated-tagged articles
~1 week · Human + Agent
5
Interlinking & Pathways
• Related Articles sections + Next Steps on all articles
• Role-pathway CardGroup blocks on all section hubs
• 'You Are Here' breadcrumb context at top of deep articles
2–3 days · Agent (batch)
6
Rename to Slugs
• Replace 1,575 opaque numeric IDs with human-readable slugs
• Update all internal links; generate SEO redirect map
• Atomic git commit; runs after Phase 3a completes
1–2 days · Script + human review
7
Nav Rebuild — Rebuild docs.json to implement 12-pillar IA; validate all file references; handle orphaned articles · 2–3 days · Agent + Human
Phases 3a & 3b/5 run in parallel after Phase 1. Phase 6 (rename) runs after 3a to avoid renaming active files.
Phase 1–2
Complete
Phase 3a
2–3 weeks
Phase 3b–5
~1 week (parallel)
Phase 6–7
3–5 days
TOTAL
6–8 weeks

## Slide 7
Key Risks & Open Decisions
Risks & Mitigations
Broken internal links after slug rename
Link-updater script + nav validator (exit 1 on any broken ref) before deploy
SEO / bookmarks broken by migration
Full redirect map generated before rename runs; maintained in Mintlify config
Sub-agents can't create new files
Net-new articles authored in main session only; agents use Edit on existing files
Merges accidentally lose unique content
Merge agents diff source articles first; all decisions require human review
Style drift in new articles
All new articles go through new-kb-article / new-overview-article skill
Legacy content removed too aggressively
Articles archived (not deleted); removals are additive nav moves, not deletions
Open Decisions (9 Require Sign-off)
D1
Workbench 4 articles (37) — archive?
Owner: You · Recommend: Archive — EOL product
D2
Projects & Tasks (10) — still active vs. Workflows?
Owner: You / PM · Check if feature still maintained
D3
Premium Apps (65) — audit for currency?
Owner: You / PM · Many may be outdated Appstore apps
D4
'Build Your First Dashboard' — move to Analyze pillar?
Owner: You · Recommend: Yes — currently misplaced
D5
'Intro to Domo' (000005874) — keep alongside new What is Domo?
Owner: You · Recommend: Keep as deep-dive companion
D6
Develop & Integrate scope — KB vs. developer.domo.com?
Owner: Dev PM · Clarify developer portal boundary
D7
Data Models (1 article, Beta) — expand or hold?
Owner: You / PM · Recommend: Hold until feature ships
D8
Instance Settings (39) — sub-group or keep flat?
Owner: You · Recommend: Keep flat for now
D9
Which DataSet Management articles move to Manage Data?
Owner: You / PM · Pipeline stays; governance articles move

## Slide 8
Next Steps
Phases 1 & 2 Complete — Audit done, IA spec approved, article mapping generated. Ready for Phase 3a.
Immediate — This Sprint
Resolve 9 open decisions (D1–D9) to unblock Phase 7 nav rebuild
Get PM sign-off on 4 PM-required articles before drafting
Begin Tier 1: What is Domo? + Getting Started for Admins
Begin Tier 1: Getting Started for App Builders & Developers
Phase 3a — New Content (2–3 Weeks)
Write all ~29 synthesizable articles in priority order
Use new-kb-article or new-overview-article skill for each
Add each to nav with add-to-nav skill immediately after
PM review recommended before publishing Tier 1 articles
Phase 3b–5 — Bulk Agent Work (Parallel)
Agent batch: add concept intros to ~200 articles missing them
Agent batch: add Next Steps + Related Articles to all articles
Consolidate & retire: merge Workbench versions, archive legacy
Add role-pathway hub cards and breadcrumb context lines
Success Metrics:
335 groups → 12 pillars
0 → 29 hub/concept articles
4 → 6 role-based guides
1,575 IDs → readable slugs
Every article has Next Steps